## Education
Education Event Organization Checklist: _________________________________________________
CHAMPION: _______________________________________ INITIAL DATE
Find suitable dates for event, check competitive events, and national holiday calendar carefully and personnel calendars
Hold Conceptualizing Meeting with Leadership team
Review agenda from previous event or draft a preliminary agenda
Establish suggested deadline dates, once confirmed add to Deadline section of Upcoming Events List
Set up new event folder on corporate server
Create new/Update event briefing doc – When completed save a copy in the main event folder (not in a specific year) and send a copy to: Leadership & Relevant Team
Book appropiate staff for event on their calendar
Finalize hotel contract/room block – must be signed and approved the appropritate manager.*
Ask hotel for an accommodation link and room rate expiration date. Alternatively, a hotel booking form doc or a code. If new hotel, request floorplans and agree to floorplan*
Draw up a new budget spreadsheet
Input all deposits and payments into Event Budget Form
Forward paid invoices to accounting team.
Set up Marketing requirements & design brief document
Create new/update project with design briefing document with the first task request
Marketing: Set up online registration link & webpage
Gather publications & relevant support material (Used for emails and website)
Business Development: Pull previous attendee list (calls, personal emails, notes regarding the event)
Optional: Marketing: Press Release Update & relevant websites with event information
Event Organization
1 year to 6 months: ___________________________________________
Begin reserving event arrangements (dinner, hotel, flights, catering, etc)
Consider email promotion for upcoming events & reminder. Schedule emails for future promotions w/ the following in mind:
Liaise with relevant team members to see if there is anyone from:
From previous event to approach to present
Business Development: Create Postal & Start pulling lists to send to
Media Promo: LinkedIn: Find relevant groups - Draft and email an announcement for the presence of event to relevant team members Twitter: Post tweet announcing Team's event. Newsletter/Email Content: Send to Marketing team. Launch advert / Save the Date
Review event agenda for new amendments & submit agenda revamp to Marketing
If event has golf, contact the course and have a contract drafted.*
*Make sure agenda has golf verbiage (and that hotel is pay your way, if applicable)*
Ask for speaker bios to be added to webpage
Ensure the attendee spreadsheet is fully up to date.
6 to 3 months: ___________________________________________
Team Midway Meeting: Practice Presentations w/ relevant team members present!
Agenda release: _____________ Email Announcement: _____________________
Upload agenda to webpages
Agenda Release Email: SEND SEPARATE EMAILS TO:
Email to all registered attendees – share with their colleagues
Email to event prospects – launching program
Email to partnered companies/sponsors – asking for customer / client lists
Email to previous attendees (for already established events) - share with their colleagues
Update Conformation Email from registration info to reflect current agenda: Hotel information, additional instructions, social events
Have Case Studies Approved & Finalized: _______________________*
Media Promo: LinkedIn: Draft & email an announcement for relevant staff members to post. Twitter: post agenda annoucement. Newsletter/Email Content: Send to Marketing team. Launch advert / Agenda announcement
Work with Marketing & relevant team members on event preview for website marketing and press release
Optional: Press release update & relevant promotional websites*
Consider email promotion and schedule emails on Marketing Email Schedule (complete mailing sheets /email planner). Aim to send one every 3 weeks.
Update break slides to include upcoming events & agenda availability
Postal Mailing: Work with Marketing to write the Postal Letter/Postcard and have proofed - Run merge, print, & seal. Schedule pick up. Send one to a staffer to ensure delivery!
Ensure budget spreadsheet is up to date
Ensure the attendee spreadsheet is fully up to date.
3 to 2 months: ___________________________________________
Team Quaterly Meeting
Postcard Announcement: __________________ Agenda release: _____________ Email Announcement: _____________________
Consider email promotion and schedule emails in on Marketing Email Schedule (and complete mailing sheets / email planner).
Discuss Folder/Packets number with Marketing. Submit design brief form to begin scheduling content edits & print
Check in w/ Leadership Team regarding one-on-one status of event. Identify problem areas & how to resolve
Review team's calendars & schedules to ensure no staff changes, flight changes, etc. Update as necessary
Send team members an email reminder for Presentations. Schedule assistance as necessary
All Edits to Presentation Slides Sent to Marketing
Send hotel & venues shipping details, instructions, electricity forms, etc. material needed in prep for event.
Media Promo: LinkedIn: Draft & email an announcement for relevant staff members to post. Twitter: post around the corner annoucement. Newsletter/Email Content: Send to Marketing team. Launch advert / Agenda announcement
Ensure budget spreadsheet is current and on track
Ensure attendee spreadsheet is fully up to date.
8 to 6 weeks: ___________________________________________
Event Team Meeting: Practice presentations V2
Consider email promotion and schedule emails in on Marketing Email Schedule (and complete mailing sheets / email planner). Promote "around the corner" excitement
Compare attendees list w/ handouts/packets/folders and update as necessary. Inform Marketing if changes need to be made to material and/or numbers
Begin tracking presentation turn-ins. Final Presentation Deadline: _______________________
Take stock of materials for handouts/packets. Ensure we have enough materials and order more of what we don't have:
Update Housekeeping Items page. Contact relevant parties for updated information.
Pull attendee list for name badges / name tents. Send to Marketing
Submit Marketing design brief to print off & put together case studies
Optional: Gather information from attendees asking for travel plans, setting one-on-ones, food allergies, etc.
Chase missing presentations, bios, marketing materials, etc.
Ensure budget spreadsheet is up to date
Ensure attendee spreadsheet is fully up to date.
5 to 4 weeks: ___________________________________________
Review team's calendars & schedules to ensure no staff changes, flight changes, etc. Update as necessary
Call to finalize last details with venues, hotels, caterings, etc.
Chase missing presentations, bios, marketing materials, etc.
Finalize Case Studies Books (+ 3-5 extra)
Check database for special events (B-days, Anniversaries, etc.) going on during event
Review "expected hotel F&B spend/budget" on hotel contract & pick menus. Update Budget excel as necessary
Contact relevant hotel & venues to receive & pick menu options. Ask for updated invoices
Request updated attendee rooming list, check for people not registered and chase them – don’t forget to send a reminder email to attendees outside of room block.
Optional: Confirm where all shipped materials will be stored.
Confirm Direct billing
Media Promo: LinkedIn: Draft & email an announcement for relevant staff members to post. Twitter: post social events. Newsletter/Email Content: Send to Marketing team. Promote social dinners & comradarie
Ensure budget spreadsheet is up to date
Ensure attendee spreadsheet is fully up to date.
3 to 2 weeks: ___________________________________________
Prepare venue schedules, including dietary requirements, A/V requirements, and floor plan. Send a pdf to relevant venues. Confirm event orders (BEOs) with hotel.
Send final guest list to hotel. Ask for copy of room block & save in event folder*
Confirm A/V needs w/ venues
Final Presentation Edits to Marketing: _______________
Create name tags & name tents (2 sets): __________________
Confirm that we have lanyard & badge stock in inventory, ask Marketing to place order if needed
Create packets/folders w/ relevant materials
If contract for next local's event is signed, send Marketing design brief for a ‘Save the date’ and prepare a final slide for the event with the following event's dates and location. Also, to prepare the info flyer for the event to distribute.
Ensure budget spreadsheet is up to date
Ensure attendee spreadsheet is fully up to date.
2 to 1 week: ___________________________________________
Final Team Check In Meeting. Note updated material that missed presentation cutoff date.
Presentation dry run practice
Load presentations on flash drives during meeting
Load final presentations to back up USB for presenters. Print hard copies as needed
Determine how packets/folders are being transferred to meeting venues
Gather presentation materials (see separate checklist) / Determine which presentation kit will be used at event: ___________________
Media Promo: LinkedIn: Draft & email an announcement for relevant staff members to post. Twitter: post Last Minute Registration. Newsletter/Email Content: Send to Marketing team. Promote last minute registration
Optional: Prepare Welcome Sides
Prepare the Survey Monkey questionnaire & hard copy with template
Create email with Questionnaire link and schedule to send to all attendees around 11am (local time) on the last day of event
Send email with agenda and schedule to attendees w/ relevant contact info
Email Marketing for final PDFs of handouts.
Give final count for dinner reservations (and to other venues if needed)
Prepare Relevant Staff Schedule, have proofed by Presenting Partner, and send pdf version to attending team
Contact hotel and check and double check that the boxes have arrived
Have a 15 min meeting with attending team to discuss the schedule, venues, attendees, expectations, and anticipations
Test presentations with Marketing (send email to any speakers with issues in their presentation). Make note of PPT's with video or sound
Have you got something to share? LinkedIn, Twitter, event News
Ensure you have spare name badges, print more if needed
Copy the Presentation for Breaks, check it is up to date, save in Back up USB
Optional: Print off what to take to event checklist and start packing – check off with team member
Ship event materials (No later than 5 business days before event). Request tracking numbers from suppliers (for ordered materials, gifts, etc. if necessary)
Send Hotel any tracking numbers. Also confirm via email that all charges for Regal staff are being directed to the master bill and confirm final guarantees.
Ensure budget spreadsheet is up to date
Ensure attendee spreadsheet is fully up to date.
LAST DAY: ___________________________________________
Check in for your flights*
Print and process any late attendee name badges / tents
Load event folder to relevant laptops – Remember to sign in to DropBox accounts in the office before travelling to ensure access to event folder materials.
Check off final items on what to take to event checklist
Print control sheet for registration
Pack relevant paper materials in folder & prep roller bag
Ensure budget spreadsheet is up to date
Ensure attendee spreadsheet is fully up to date.
POST EVENT: ___________________________________________
Schedule follow up meeting w/ attended staff*
Call all no-shows and charge accordingly
Schedule follow up as requested with attendees
Update social media with a posts
Update upcoming events master list w/ final attendee number
Receive and pay for last invoice from venue
Receive and pay for last invoice from hotel, taxi, etc.
Send invoices to accounting team or book keeper
Review w/ Leadership the state of the event and impact
Submit registration sheet to compliance
For Internal use only
Regal Investment Advisors, LLC, DBA LionShare (hereinafter "LionShare") is an SEC registered investment advisor. Registration with the SEC does not imnply any level of skill or training.
- Dates should fall between now and the end of the first deadline
- Emails should be sent every 3 to 4 weeks
- Ensure you log the information (mailing sheet / email planner)
- Other marketing emails & postals going out
- Previous events to approach about attending
- The prior year's locals who weren't suitable then but would be for current year
- The industry to target
- Previous events/referrals to contact
- Notebooks, foam desk animals, pen
- Case study
- Fact Sheet
- Marketing Commentary
- Any articles
- Housekeeping Items (Map, Venue passwords, Addresses, etc.) - Upcoming special/relationship/LIA events flyer
- Money Management weekly email - Optional: Upcoming "see us at..." flyer
- Flash drives